## Draft May 2012
| Proj Id | 2008-09 | 2009-01 | 2009-05 | 2011-01 | 2011-05 | 2011-09 | 2012-01 | 2012-05 | 2012-09 | 2013-01 | 2013-05 | 2013-09 | 2014-01 | 2014-05 | 2014-09 | status
V3 Patient Administration
Person | 576 |  |  |  | W | W | D | --> | --> | W | --> | D | --> | --> | --> | N | Last Ballot: DSTU ballot 1 May 2010
Identity Document | ?? |  |  | W? | W | W | D | --> | --> | W | --> | D | --> | --> | --> | N | Last Ballot: Domain Level DSTU Ballot 2 - September 2009
Patient | 576 |  |  | W | W | D | --> | --> | --> | W | --> | D | --> | --> | --> | N | Last Ballot: DSTU Ballot 1 - May 2011
Service Delivery Location | [16 empty] | Last Ballot: Domain Level DSTU Ballot 2 - September 2009 | bar: W? W
Ambulatory Encounter | 489/736 |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Inpatient Encounter |  |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Emergency Encounter |  |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Home Health Encounter |  |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Short Stay Encounter |  |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter Location |  |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter Provider |  |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter Organization |  |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter Queries |  |  |  | W | W | D | --> | --> | --> | D | --> | --> | N |  |  |  | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter R2 |  |  |  | W --> --> --> --> --> --> --> --> -->: W; W --> --> --> --> --> --> --> --> -->: -->; W N N N N N N N N N: --> | D | --> | -->
V3 Registries | bar: W W W W W W W W W W; W --> --> --> --> --> --> --> --> -->; W --> --> --> --> --> --> --> --> -->; W --> --> --> --> --> --> --> --> -->; W N N N N N N N N N
Real Time Location System | 491 | bar: W W W W W W W W W W
Person (from PA) | 576 |  |  | W W W W W W W W W W: -->; W D D D D D D D D D: -->; W --> --> --> --> --> --> --> --> -->: N
Identity Document (from PA) | ?? | bar: W W W W W W W W W W
Patient (from PA) | ?? | bar: W W W W W W W W W W; W --> --> --> --> --> --> --> --> -->
Service Delivery Location (from PA) |  |  |  | W | D | --> | --> | --> | N
Provider Registry (from PM) | 359 |  | D | W | D | --> | --> | --> | N | [7 empty] | Last Ballot: DSTU Ballot 1 - January 2009. Re-enter Jan 2009 material in the current ballot and move to DSTU when ballot comments from 2009 are resolved.
Organization Registry (from PM) | 360 |  | D | W | D | --> | --> | --> | N | [7 empty] | Last Ballot: DSTU Ballot 1 - January 2009. Re-enter Jan 2009 material in the current ballot and move to DSTU when ballot comments from 2009 are resolved. Need to retrieve the ballot reconsiliation package from the Jan 2009 ballot from Don.
Human Resource (from PM)
Regulatory (from PM)
Provider Registry Services |  |  |  | W W W W W W W W W W: D; W D D D D D D D D D: -->; W --> --> --> --> --> --> --> --> -->: -->; W --> --> --> --> --> --> --> --> -->: -->; W --> --> --> --> --> --> --> --> -->: N |  |  |  | No formal project scope statement was submitted
Registry Enhancements for Social Services | 490 |  | W | bar: W W W W W W W W W W
Interdependant Registries | 725 | bar: W D D D D D D D D D
V3 Personnel Management (C)
Human Resource
Regulatory
V3 Personnel Management
Provider Registry (from PM) | 359 |  | D | W | W | W | D | --> | --> | N | [6 empty] | Last Ballot: DSTU Ballot 1 - January 2009
Organization Registry (from PM) | 360 |  | D | W | W | W | D | --> | --> | N | [6 empty] | Last Ballot: DSTU Ballot 1 - January 2010
V3 Scheduling & Logistics | 292
Appointment | 292 |  |  |  | W | W | W | D | --> | --> | N | [5 empty] | Last Ballot: DSTU Ballot 1 - January 2009. Re-enter Jan 2009 material in the current ballot and move to DSTU when ballot comments from 2009 are resolved. Need to retrieve the ballot reconsiliation package from the Jan 2009 ballot from Don.
Slot |  |  |  |  | W | W | W | D | --> | --> | N | [5 empty] | Last Ballot: DSTU Ballot 1 - January 2009. Re-enter Jan 2009 material in the current ballot and move to DSTU when ballot comments from 2009 are resolved. Need to retrieve the ballot reconsiliation package from the Jan 2009 ballot from Don.
V3 CMETs
PA CMETs | 361 | N | D D: N; W W: W; D D: D
PM CMETs |  |  |  |  | W | W | D | --> | --> | N
SC CMETs | 459 |  | D D: W; W W: -->; W W: N
HL7 V2.7
Chapter 3 |  | N | bar: D D
Chapter 8 |  | N
Chapter 10 |  | N | bar: D D
Chapter 15 |  | N | bar: D D
Last revised: 2010-02-01
Note on B4: Gregg Seppala: - Need two or more named implementers to work on DSTU 2 check with Rene jongeneel: Implementers available, create new Project
Note on B5: Gregg Seppala: - Don't have go-forward plan yet - Need two or more implenters - Need feedback from DSTU - check Klaus jongeneel: Check JGZ implementers with Alexander
Note on B6: jongeneel: a new project scope statement will be presented bij Canada in May 2013. No record was found of the project or requirements for the past work plan
Note on G7: Gregg Seppala: 2009-05-23 Extended DSTU trial period to 12 months, pushing out possible normative ballot
Note on I7: Irma Jongeneel: introduced new DSTU time of 1 year to make sure the collapsing encounter topic doesnt have unexpected issues
Note on K7: Gregg Seppala: 2009-05-23 Extended DSTU trial period to 12 months, pushing out possible normative ballot
Note on M7: Irma Jongeneel: introduced new DSTU time of 1 year to make sure the collapsing encounter topic doesnt have unexpected issues
Note on N7: jongeneel: this should be 2013-09
Note on A16: jongeneel: Encounter R2 to be based on Harmonized DMIM for PC and PA. Implementers from Norway.
Note on B20: Gregg Seppala: - Need to get revised requirements from current implementers - Need two or more named implementers to work on DSTU 2 check with Rene
Note on B21: Gregg Seppala: - Don't have go-forward plan yet - Need two or more implenters - Need feedback from DSTU - check Klaus
Note on A23: Gregg Seppala: - Harmonize dynamic model - Consider two sets of application roles for two dynamic model patterns - gather requirements from additional realms
Note on B23: Gregg Seppala: complete 359 and 360 and add new Project for Personnel Mgt
Note on B27: Gregg Seppala: New project propsal considered at May wgm
Note on B28: Gregg Seppala: Need two or more implenters who express interest in this project, Yvonne
Note on G29: jongeneel: DAM ballot in May 2011, May 2012 working on ballot recons.
Note on A34: Gregg Seppala: - Harmonize dynamic model - Consider two sets of application roles for two dynamic model patterns - gather requirements from additional realms
Note on B34: Gregg Seppala: complete 359 and 360 and add new Project for Personnel Mgt
Note on B36: Gregg Seppala: Set to On Hold Waiting for Resources
Note on E42: Gregg Seppala: Changed D to C; decided to verify requirements before balloting; moved rest of cycle out by one meeting

## 2009-2013
| Proj Id | 2008-09 | 2009-01 | 2009-05 | 2009-09 | 2010-01 | 2010-05 | 2010-10 | 2011-01 | 2011-05 | 2011-09 | 2012-01 | 2012-05 | 2012-09 | 2013-01 | status
V3 Patient Administration
Person | 576 |  |  |  |  | W | D | --> | W | W | D | --> | --> | N |  | Last Ballot: DSTU ballot 1 May 2010
Identity Document | ?? |  |  | W? |  |  | withdraw? |  | W | W | D | --> | --> | N |  | Last Ballot: Domain Level DSTU Ballot 2 - September 2009
Patient | 576 |  |  | W |  |  |  |  | W | D | --> | --> | --> | N |  | Last Ballot: DSTU Ballot 1 - May 2011
Service Delivery Location |  |  |  | W |  |  | peer rev | W | W | W | D | --> | --> | N |  | Last Ballot: Domain Level DSTU Ballot 2 - September 2009
Ambulatory Encounter | 489 |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
Inpatient Encounter |  |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
Emergency Encounter |  |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
Home Health Encounter |  |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
Short Stay Encounter |  |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter Location |  |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter Provider |  |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter Organization |  |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
Encounter Queries |  |  |  | W | D | --> | --> | --> | W | D | --> | D | D | --> | N | Last Ballot: DSTU Ballot 2 - Jan 2012
V3 Registries
Real Time Location System | 491 | bar: W W W W W W W W W to --> --> --> --> --> --> --> --> -->
Person (from PA) | 576 |  |  | --> --> --> --> --> --> --> --> -->: W; --> --> --> --> --> --> --> --> -->: D; --> --> --> --> --> --> --> --> -->: -->; W W W W W W W W W: -->; D D D D D D D D D: -->; --> --> --> --> --> --> --> --> -->: N
Identity Document (from PA) | ?? |  |  | W W W W W W W W W: W?; --> --> --> --> --> --> --> --> -->: withdraw?
Patient (from PA) | ?? | bar: W W W W W W W W W; --> --> --> --> --> --> --> --> -->
Service Delivery Location (from PA) |  |  |  | W |  |  | peer rev | W | D | --> | --> | --> | N
Provider Registry (from PM) | 359 |  | D | W |  | W | peer rev | W | D | --> | --> | --> | N |  |  | Last Ballot: DSTU Ballot 1 - January 2009. Re-enter Jan 2009 material in the current ballot and move to DSTU when ballot comments from 2009 are resolved.
Organization Registry (from PM) | 360 |  | D | W |  | W | peer rev | W | D | --> | --> | --> | N |  |  | Last Ballot: DSTU Ballot 1 - January 2009. Re-enter Jan 2009 material in the current ballot and move to DSTU when ballot comments from 2009 are resolved. Need to retrieve the ballot reconsiliation package from the Jan 2009 ballot from Don.
Human Resource (from PM)
Regulatory (from PM)
Provider Registry Services | [5 empty] | W | W | W | D | --> | --> | --> | N |  |  | No formal project scope statement was submitted
Registry Enhancements for Social Services | 490 |  | W | W | W | W: C/done |  | x
Interdependant Registries | 725 | bar: -->
V3 Personnel Management (C) | bar: W; D; -->
Human Resource
Regulatory
V3 Personnel Management | bar: W; D; -->
Provider Registry (from PM) | 359 |  | D | W |  | W | peer rev | W | W | W | D | --> | --> | N |  | Last Ballot: DSTU Ballot 1 - January 2009
Organization Registry (from PM) | 360 |  | D | W |  | W | peer rev | W | W | W | D | --> | --> | N |  | Last Ballot: DSTU Ballot 1 - January 2010
V3 Scheduling & Logistics | 292 | bar: W; D; -->; N
Appointment | 292 | [7 empty] | W | W | W | D | --> | --> | N | Last Ballot: DSTU Ballot 1 - January 2009. Re-enter Jan 2009 material in the current ballot and move to DSTU when ballot comments from 2009 are resolved. Need to retrieve the ballot reconsiliation package from the Jan 2009 ballot from Don.
Slot | [8 empty] | W | W | W | D | --> | --> | N | Last Ballot: DSTU Ballot 1 - January 2009. Re-enter Jan 2009 material in the current ballot and move to DSTU when ballot comments from 2009 are resolved. Need to retrieve the ballot reconsiliation package from the Jan 2009 ballot from Don.
V3 CMETs | bar: W; D; -->; N
PA CMETs | 361 | N | N |  |  | W: N; -->: W; -->: D
PM CMETs | [7 empty] | W | W | W | D | --> | --> | N
SC CMETs | 459 |  | W |  |  | D | --> | --> | --> | N
HL7 V2.7 | bar: W; D; -->; N
Chapter 3 |  | N | N
Chapter 8 |  | N
Chapter 10 |  | N | N
Chapter 15 |  | N | N
Last revised: 2010-02-01 | [5 empty] | W: Key - Activity at WGM
[7 empty] | W | Work Item for WGM
[7 empty] | C | Draft for Comment ballot review
[7 empty] | D | DSTU ballot reconciliation
[7 empty] | N | Normative ballot reconciliation
Note on B4: Gregg Seppala: - Need two or more named implementers to work on DSTU 2 check with Rene jongeneel: Implementers available, create new Project
Note on B5: Gregg Seppala: - Don't have go-forward plan yet - Need two or more implenters - Need feedback from DSTU - check Klaus jongeneel: Check JGZ implementers with Alexander
Note on B6: jongeneel: a new project scope statement will be presented bij Canada in May 2013. No record was found of the project or requirements for the past work plan
Note on I6: Gregg Seppala: Will need to bring ballot ready for review given short turnaround for Jan ballot
Note on K7: Gregg Seppala: 2009-05-23 Extended DSTU trial period to 12 months, pushing out possible normative ballot
Note on M7: Gregg Seppala: 2009-05-23 Extended DSTU trial period to 12 months, pushing out possible normative ballot
Note on N7: jongeneel: Encounter topic will be moved to DSTU based on resolving the May Ballot
Note on O7: Irma Jongeneel: introduced new DSTU time of 1 year to make sure the collapsing encounter topic doesnt have unexpected issues
Note on P7: jongeneel: this should be 2013-09
Note on B19: Gregg Seppala: - Need to get revised requirements from current implementers - Need two or more named implementers to work on DSTU 2 check with Rene
Note on B20: Gregg Seppala: - Don't have go-forward plan yet - Need two or more implenters - Need feedback from DSTU - check Klaus
Note on I21: Gregg Seppala: Will need to bring ballot ready for review given short turnaround for Jan ballot
Note on A22: Gregg Seppala: - Harmonize dynamic model - Consider two sets of application roles for two dynamic model patterns - gather requirements from additional realms
Note on B22: Gregg Seppala: complete 359 and 360 and add new Project for Personnel Mgt
Note on B26: Gregg Seppala: New project propsal considered at May wgm
Note on B27: Gregg Seppala: Need two or more implenters who express interest in this project, Yvonne
Note on F27: Gregg Seppala: 2009-05-22 changed from C to W
Note on G27: Gregg Seppala: 2009-05-22, at May WGM decided to review material at Sept WGM before publishing
Note on K28: jongeneel: DAM ballot in May 2011, May 2012 working on ballot recons.
Note on A33: Gregg Seppala: - Harmonize dynamic model - Consider two sets of application roles for two dynamic model patterns - gather requirements from additional realms
Note on B33: Gregg Seppala: complete 359 and 360 and add new Project for Personnel Mgt
Note on B35: Gregg Seppala: Set to On Hold Waiting for Resources
Note on E41: Gregg Seppala: Changed D to C; decided to verify requirements before balloting; moved rest of cycle out by one meeting

## Updated 10-2015
| Proj Id | FMM DSTU2 | Status | 2008-09 | 2009-01 | 2009-05 | 2011-01 | 2011-05 | 2011-09 | 2012-01 | 2012-05 | 2012-09 | 2013-01 | 2013-05 | 2013-09 | 2014-01 | 2014-05 | 2014-09 | 2015-01 | 2015-05 | 2015-10 | 2016-01 | 2016-05 | 2016-09 | 2017-01 | 2017-05 | 2017-09
V3 Registries
Person R2 | 576 |  | DSTU |  |  |  | W | W | D | --> | --> | W | --> |  |  |  | N
Patient R2 | 576 |  | DSTU |  |  | W | W | D | --> | --> | --> | W | --> |  |  |  | N
Service Delivery Location | 650 |  | On hold |  |  | W
PA / PHER harmanization | tba |  | Not started |  |  | W | [11 empty] | W
V3 Encounter
Encounter R2 | 1029 |  | Normative | [12 empty] | N
Interdependant Registries | 725 |  | Canceled |  |  |  |  | W
V3 Personnel Management (C)
Personnel Management | 986 |  | Reaffirm | [12 empty] | R
V3 Scheduling
Appointment | 987 |  | Normative |  |  |  | W | W | W | D | --> | --> | N |  |  |  | N
Slot |  |  | Normative |  |  |  | W | W | W | D | --> | --> | N |  |  |  | N
V3 CMETs
PA CMETs | 361 |  | Canceled | N | N |  |  | W | D |  |  |  |  | N
PM CMETs | 574 |  | Canceled |  |  |  | W | W | D | --> | -->
SC CMETs | 459 |  | Canceled |  | W |  | --> | N
HL7 V2.x
Chapter 3 |  |  | Normative | N | N
Chapter 8 |  |  | Normative | N
Chapter 10 |  |  | Normative | N | N
Chapter 15 |  |  | Normative | N | N
FHIR
Patient | 925 | 3 | DSTU | [8 empty] | W | C |  | C | D |  |  |  | W | W | W | W | W |  | N
Practitioner |  | 1 | DSTU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | W |  | N
Organization |  | 1 | DSTU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | W |  | N
Group |  | 1 | DSTU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | W |  | N
RelatedPerson |  | 1 | DSTU | [11 empty] | C | D |  |  |  | W | W | W | W | W |  | N
Encounter |  | 1 | DSTU | [11 empty] | C | D |  |  |  | W | W | W | W | W |  | N
Location |  | 1 | DSTU | [12 empty] | D |  |  |  | W | W | W | W | W |  | N
HealthcareService | 1123 | 1 | DSTU 2 | [12 empty] | W | W | W | D | W | W | W | W | W | W | N
Schedule |  | 1 | DSTU 2 | [12 empty] | W | W | W | D | W | W | W | W | W | W | N
Appointment |  | 1 | DSTU 2 | [12 empty] | W | W | W | D | W | W | W | W | W | W | N
Slot |  | 1 | DSTU 2 | [12 empty] | W | W | W | D | W | W | W | W | W | W | N
AppointmentResponse |  | 1 | DSTU 2 | [12 empty] | W | W | W | D | W | W | W | W | W | W | N
EpisodeOfCare |  | 1 | DSTU 2 | [12 empty] | W | W | W | D | W | W | W | W | W | W | N
BillableItem |  |  | DSTU 2 | [18 empty] | W | W | W | W | N
Account |  |  | DSTU 2 | [18 empty] | W | W | W | W | N
Profiles and implementation guidelines |  |  | DSTU 2 | [18 empty] | W | W | W | W | N
OTHERS
HAVE/TEP project |  |  | Planning | [18 empty] | W | B
Key - Activity at WGM
[16 empty] | W | Work Item for WGM
[16 empty] | C | Draft for Comment ballot review
[16 empty] | D | DSTU ballot reconciliation
[16 empty] | N | Normative ballot reconciliation
[16 empty] | R | Reaffirm ballot reconciliation
Note on S6: ijongeneel: Analyse content PHER domain. Based on outcome might lead to update PA DMIM and CMET's
Note on I9: jongeneel: DAM ballot in May 2011, May 2012 working on ballot recons.
Note on G18: Gregg Seppala: Changed D to C; decided to verify requirements before balloting; moved rest of cycle out by one meeting

## Updated 5-2016
| Proj Id | FMM DSTU2 | Status | 2008-09 | 2009-01 | 2009-05 | 2011-01 | 2011-05 | 2011-09 | 2012-01 | 2012-05 | 2012-09 | 2013-01 | 2013-05 | 2013-09 | 2014-01 | 2014-05 | 2014-09 | 2015-01 | 2015-05 | 2015-10 | 2016-01 | 2016-05 | 2016-09 | 2017-01 | 2017-05 | 2017-09
V3 Registries
Person R2 | 576 |  | DSTU |  |  |  | W | W | D | --> | --> | W | --> |  |  |  | N
Patient R2 | 576 |  | DSTU |  |  | W | W | D | --> | --> | --> | W | --> |  |  |  | N
Service Delivery Location | 650 |  | On hold |  |  | W
PA / PHER harmanization | tba |  | Not started |  |  | W | [11 empty] | W
V3 Encounter
Encounter R2 | 1029 |  | Normative | [12 empty] | N
Interdependant Registries | 725 |  | Canceled |  |  |  |  | W
V3 Personnel Management (C)
Personnel Management | 986 |  | Reaffirm | [12 empty] | R
V3 Scheduling
Appointment | 987 |  | Normative |  |  |  | W | W | W | D | --> | --> | N |  |  |  | N
Slot |  |  | Normative |  |  |  | W | W | W | D | --> | --> | N |  |  |  | N
V3 CMETs
PA CMETs | 361 |  | Canceled | N | N |  |  | W | D |  |  |  |  | N
PM CMETs | 574 |  | Canceled |  |  |  | W | W | D | --> | -->
SC CMETs | 459 |  | Canceled |  | W |  | --> | N
HL7 V2.9
Chapter 3 | 773 |  | Normative | N | N | [16 empty] | W | N
Chapter 8 | 773 |  | Normative | N | [17 empty] | W | N
Chapter 10 | 773 |  | Normative | N | N | [16 empty] | W | N
Chapter 15 | 773 |  | Normative | N | N | [16 empty] | W | N
FHIR
Patient | 925 | 3 | STU | [8 empty] | W | C |  | C | D |  |  |  | W | W | W | W | B |  | N
Practitioner |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | B |  | N
Organization |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | B |  | N
Group |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | B |  | N
RelatedPerson |  | 1 | STU | [11 empty] | C | D |  |  |  | W | W | W | W | B |  | N
Encounter |  | 1 | STU | [11 empty] | C | D |  |  |  | W | W | W | W | B |  | N
Location |  | 1 | STU | [12 empty] | D |  |  |  | W | W | W | W | B |  | N
HealthcareService | 1123 | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | B | W | N
Schedule |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | B | W | N
Appointment |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | B | W | N
Slot |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | B | W | N
AppointmentResponse |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | B | W | N
EpisodeOfCare |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | B | W | N
BillableItem | bar: W W W W W W to N N N N N N
Account |  |  | STU | [12 empty] | W W W W W W: W; W W W W W W: W; B B B B B B: B; W W W W W W: W; N N N N N N: N
Profiles and implementation guidelines | bar: W W W W W W to N N N N N N
OTHERS
HAVE/TEP project |  |  | Planning | bar: W W W W W W to W W W W W W
Key - Activity at WGM
[16 empty] | W | Work Item for WGM
[16 empty] | C | Comment ballot review
[16 empty] | D | Draft Standard for Trial Use
[16 empty] | N | Normative ballot reconciliation
[16 empty] | R | Reaffirm ballot reconciliation
Note on S6: ijongeneel: Analyse content PHER domain. Based on outcome might lead to update PA DMIM and CMET's
Note on I9: jongeneel: DAM ballot in May 2011, May 2012 working on ballot recons.
Note on G18: Gregg Seppala: Changed D to C; decided to verify requirements before balloting; moved rest of cycle out by one meeting

## Updated 9-2016
| Proj Id | FMM DSTU2 | Status | 2008-09 | 2009-01 | 2009-05 | 2011-01 | 2011-05 | 2011-09 | 2012-01 | 2012-05 | 2012-09 | 2013-01 | 2013-05 | 2013-09 | 2014-01 | 2014-05 | 2014-09 | 2015-01 | 2015-05 | 2015-10 | 2016-01 | 2016-05 | 2016-09 | 2017-01 | 2017-05 | 2017-09 | 2018-01 | 2018-05 | 2018-09
V3 Registries
Person R2 | 576 |  | DSTU |  |  |  | W | W | D | --> | --> | W | --> |  |  |  | N
Patient R2 | 576 |  | DSTU |  |  | W | W | D | --> | --> | --> | W | --> |  |  |  | N
Service Delivery Location | 650 |  | On hold |  |  | W
PA / PHER harmanization | tba |  | Not started |  |  | W | [11 empty] | W
V3 Encounter
Encounter R2 | 1029 |  | Normative | [12 empty] | N
Interdependant Registries | 725 |  | Canceled |  |  |  |  | W
V3 Personnel Management (C)
Personnel Management | 986 |  | Reaffirm | [12 empty] | R
V3 Scheduling
Appointment | 987 |  | Normative |  |  |  | W | W | W | D | --> | --> | N |  |  |  | N
Slot |  |  | Normative |  |  |  | W | W | W | D | --> | --> | N |  |  |  | N
V3 CMETs
PA CMETs | 361 |  | Canceled | N | N |  |  | W | D |  |  |  |  | N
PM CMETs | 574 |  | Canceled |  |  |  | W | W | D | --> | -->
SC CMETs | 459 |  | Canceled |  | W |  | --> | N
HL7 V2.9
Chapter 3 | 773 |  | Normative | N | N | [16 empty] | W | N
Chapter 8 | 773 |  | Normative | N | [17 empty] | W | N
Chapter 10 | 773 |  | Normative | N | N | [16 empty] | W | N
Chapter 15 | 773 |  | Normative | N | N | [16 empty] | W | N
FHIR
Patient | 925 | 3 | STU | [8 empty] | W | C |  | C | D |  |  |  | W | W | W | W | C |  | W | N
Practitioner |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | C | W | W | N
Organization |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | C |  | W | N
Group |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | C |  | W | C | W
Person |  | 1 | STU | [16 empty] | W | W | W | W | C |  | W | C | W
RelatedPerson |  | 1 | STU | [11 empty] | C | D |  |  |  | W | W | W | W | C | W | W | N
Encounter |  | 1 | STU | [11 empty] | C | D |  |  |  | W | W | W | W | C | W | W | N
Location |  | 1 | STU | [12 empty] | D |  |  |  | W | W | W | W | C |  | W | N
HealthcareService | 1102 | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | C | W
Schedule |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | C | W
Appointment |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | C
Slot |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | C
AppointmentResponse |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | C
EpisodeOfCare |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | C | W
BillableItem | [21 empty] | W | W | W | W | W | C | W
Endpoint |  | 0 | STU | [19 empty] | W | C | W | W | N
Account |  | 0 | STU | [18 empty] | W | W | C | W | W | C | W
Profiles and implementation guidelines | [21 empty] | W | W | W | W | W | C | W
OTHERS
HAVE/TEP project |  |  | Planning | [18 empty] | W | B |  | W
Schedulig project |  |  | Planning | [21 empty] | W
Occupational health project |  |  | Planning | [21 empty] | W
Key - Activity at WGM
W | Work Item for WGM
C | Comment ballot review
D | Draft Standard for Trial Use
N | Normative ballot reconciliation
R | Reaffirm ballot reconciliation
Note on S6: ijongeneel: Analyse content PHER domain. Based on outcome might lead to update PA DMIM and CMET's
Note on I9: jongeneel: DAM ballot in May 2011, May 2012 working on ballot recons.
Note on G18: Gregg Seppala: Changed D to C; decided to verify requirements before balloting; moved rest of cycle out by one meeting

## Update 9-2017
| Proj Id | FMM DSTU2 | Status | 2008-09 | 2009-01 | 2009-05 | 2011-01 | 2011-05 | 2011-09 | 2012-01 | 2012-05 | 2012-09 | 2013-01 | 2013-05 | 2013-09 | 2014-01 | 2014-05 | 2014-09 | 2015-01 | 2015-05 | 2015-10 | 2016-01 | 2016-05 | 2016-09 | 2017-01 | 2017-05 | 2017-09 | 2018-01 | 2018-05 | 2018-09 | 2019-01 | 2019-05
V3 Registries
Person R2 | 576 |  | DSTU |  |  |  | W | W | D | --> | --> | W | --> |  |  |  | N
Patient R2 | 576 |  | DSTU |  |  | W | W | D | --> | --> | --> | W | --> |  |  |  | N
Service Delivery Location | 650 |  | On hold |  |  | W
PA / PHER harmanization | tba |  | Not started |  |  | W | [11 empty] | W
V3 Encounter
Encounter R2 | 1029 |  | Normative | [12 empty] | N
Interdependant Registries | 725 |  | Canceled |  |  |  |  | W
V3 Personnel Management (C)
Personnel Management | 986 |  | Reaffirm | [12 empty] | R
V3 Scheduling
Appointment | 987 |  | Normative |  |  |  | W | W | W | D | --> | --> | N |  |  |  | N
Slot |  |  | Normative |  |  |  | W | W | W | D | --> | --> | N |  |  |  | N
V3 CMETs
PA CMETs | 361 |  | Canceled | N | N |  |  | W | D |  |  |  |  | N
PM CMETs | 574 |  | Canceled |  |  |  | W | W | D | --> | -->
SC CMETs | 459 |  | Canceled |  | W |  | --> | N
HL7 V2.9
Chapter 3 | 773 |  | Normative | N | N | [16 empty] | W | N
Chapter 8 | 773 |  | Normative | N | [17 empty] | W | N
Chapter 10 | 773 |  | Normative | N | N | [16 empty] | W | N
Chapter 15 | 773 |  | Normative | N | N | [16 empty] | W | N
FHIR
Patient | 925 | 3 | STU | [8 empty] | W | C |  | C | D |  |  |  | W | W | W | W | C |  | W | W | C | N
Practitioner |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | C | W | W | W | C | S | W
Organization |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | C |  | W | W | C | S | W
Group |  | 1 | STU | [9 empty] | C |  | C | D |  |  |  | W | W | W | W | C |  | W | W | C | S | W
Person |  | 1 | STU | [16 empty] | W | W | W | W | C |  | W | W | C | S | W
RelatedPerson |  | 1 | STU | [11 empty] | C | D |  |  |  | W | W | W | W | C | W | W | W | C | S | W
Encounter |  | 1 | STU | [11 empty] | C | D |  |  |  | W | W | W | W | C | W | W | W | C | S | W
Location |  | 1 | STU | [12 empty] | D |  |  |  | W | W | W | W | C |  | W | W | C | S | W
HealthcareService | 1102 | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | W | C | S | W
Schedule |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | W | C | S | W
Appointment |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | W | C | S | W
Slot |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | W | C | S | W
AppointmentResponse |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | W | C | S | W
EpisodeOfCare |  | 1 | STU | [12 empty] | W | W | W | D | W | W | W | W | C | W | W | W | C | S | W
ChargeItem | [21 empty] | W | W | W | W | W | W | C | S | W
Endpoint |  | 0 | STU | [12 empty] | W W W W W W: W; C C C C C C: C; W W W W W W: W; W W W W W W: W; W W W W W W: W; C C C C C C: C; S S S S S S: S; W W W W W W: W
Account |  | 0 | STU | [18 empty] | W | W | C | W | W | W | C | S | W
Profiles and implementation guidelines | bar: W W W W W W to W W W W W W
OTHERS
HAVE/TEP project | 1346 |  | Planning | [12 empty] | W W W W W W: W; W W W W W W: B; W W W W W W: W; W W W W W W: W; C C C C C C: W; S S S S S S: W?
Scheduling project (IG) |  |  | Planning | bar: W W W W W W to W W W W W W
Occupational health project (co-sponsor) | 1290 |  | Planning | bar: W W W W W W; W W W W W W
Provider Directories Project (IG) | 1345 |  | PSS Planning | bar: W W W W W W to W W W W W W
Key - Activity at WGM
W | Work Item for WGM
C | Comment ballot review
S/D | Standard for Trial Use
N | Normative ballot reconciliation
R | Reaffirm ballot reconciliation
Note on S6: ijongeneel: Analyse content PHER domain. Based on outcome might lead to update PA DMIM and CMET's
Note on I9: jongeneel: DAM ballot in May 2011, May 2012 working on ballot recons.
Note on G18: Gregg Seppala: Changed D to C; decided to verify requirements before balloting; moved rest of cycle out by one meeting