Health Level Seven

www.hl7.org

Change Control Process using HL7 Project Homebase

Version 1.0.1

CONTENTS

Change control using HL7 Project Homebase	3

Background	3

7.1 Overview	3

7.2 Context	3

7.3 Roles and Responsibilities	4

Submitter (Requester)	4

Evaluator	4

Modifier	5

Reviewer	5

7.4 Process and Tasks	5

7.4 Change Control Process	5

7.4: Change Control Process	5

7.4.1 Schedule work	7

7.4.1: Schedule work	8

7.5 Quality Criteria	8

Traceability to requirements	8

7.6 Tools	9

References:	18

Training	18

# Change Control Using HL7 Project Homebase

The purpose of this article is to describe the options available to HL7 members to automate issue tracking and change control in order to provide better quality standards. HL7 provides to its members an integrated web portal (HL7 Project Homebase) that supports change control, task management, surveys, release management, document management, and source control in an integrated, web-based tool. As the name indicates, HL7 Project Homebase can be used as the home page for HL7 projects and committees in a way similar to Sourceforge.net, one of the most successful open-source project hosting portals.

HL7 Project Homebase (hl7projects.hl7.nscee.edu/) is based on the GForge open-source product (www.gforge.org) that can host the artifacts of an HL7 project including the mechanism to manage the changes to those artifacts. The benefits of the Homebase portal include seamless integration of issue tracking and task management with version control and release management.  In this capacity, it can support all the phases of an HL7 standard development project.

#### Background

There is considerable overlap and confusion surrounding the change management, configuration management and change control modalities.  Change control today consists of six steps, where each step may have another process associated with it.  These start with the receipt of the Request for Change or RFC, or a Request for Service (RFS):

1. Record / Classify
2. Assess
3. Plan

4. Build / Test
5. Implement
6. Close / Gain Acceptance

### 7.1 Overview

Change control is the process to be used when requesting and managing changes for product development performed by the members of HL7.  The process will (1) facilitate communication about requested changes amongst the stakeholders of HL7, (2) provide a common process for resolving requested changes and reported problems, and (3) reduce any uncertainty surrounding the existence, state, and outcome of a change that has been requested in a work product.

### 7.2 Context

The change control process (hereafter referred to as CCP) is used in the larger context of a project life-cycle. Any HL7 standard stakeholder can submit the following types of issues to the change control system:

- Requests for requirement changes (additions, deletions, modifications, deferrals) to standards currently under development

- Reports of problems in current specifications and runtime artifacts

- Requests for enhancements in current artifacts

- Requests for new development projects and artifacts

The CCP will apply to baselined work products created or managed by the members of the HL7 committee or project, including:

- Standard artifacts that have been approved or draft for trial use

- Requirements specifications for methodology (procedures and processes)

- User and technical documentation

The following work product classes are exempted from the CCP:

- Work products that are still under development except requirements changes requested for new projects

- Interim or temporary work products created during the course of a project

- Any work products intended for individual use only

##### 7.2.1: Change Control Process Context

The following diagram provides a high-level view of the processes described in the HDF specification to support the project and product lifecycle. Managing change is an intrinsic aspect of creating and improving specifications in a collaborative environment.The key processes required by the HL7 Development Framework (HDF) are represented from a high-level as components of a larger product lifecycle process. All the processes in the HDF require a rigorous approach to managing changes (i.e., technical corrections, enhancement requests, and new standard creation) suggested to the body of HL7 standards.

Figure 7.2.1: Change Control Process Context

### 7.3 Roles and Responsibilities

The following roles and responsibilities are used within the CCP for HL7 artifacts.  Note that one individual may play multiple roles in the context of this process.

##### Submitter (Requester)

The submitter is a person, project, or committee that initiates the change request. This may be a user of a standard, a DSTU implementer, or a member of the committee or project responsible for the artifact that requires the changes.

##### Evaluator

The evaluation of a Change Request will be done by a group similar to a Change Control Board (CCB). This group may consist of the co-chairs or of a volunteer designated by the committee or project that receives the Change Request.  The Evaluator or CCB may consist of the co-chairs or a designated co-chair or a volunteer as decided by the committee or project. The committee may be Technical Committee, a Special Interest Group, or project affiliated with a committee.

##### Modifier

The person assigned to address the change request. This committee member is responsible for completing the solution required in the change request.

##### Reviewer

The reviewer is a member of a project team that is involved in reviewing an artifact that was changed in response to defect report or enhancement request.

### 7.4 Process and Tasks

This section describes the process, decision points, activities, deliverables, and tools required to support CCP.

##### 7.4.1 Change Control Process

A change is “an event that results in a new status of one or more configuration items (CI's)”, and is approved by management, is cost effective, and enhances business process changes (fixes) with a minimum risk to IT infrastructure.  The main aims of Change Management are:

- Minimal disruption

- Reduction in back-out activities

- Economic utilization of resources involved in the change

- Efficient use of resources

CCP is a formal process used to ensure a product, service or process is only modified in line with the identified necessary change. It is part of the lifecycle. It is particularly critical to the early development phase of the software development/engineering process to ensure that unnecessary requirements were not created as artifacts in the code creation phase.  Quite often unnecessary requirements and changes introduce defects which require expensive rework.  CCP has evolved to become a fundamental process in quality control too.  A change "freeze point" was introduced to suspend any further changes until after the completion of the initial project.  CCP is also used  to help determine the the impact of a change and if it introduces severe risk and/or financial consequence.  Typical examples from the computer and network environments are the upgrade of operating systems, network routing tables or the electrical power systems supporting such infrastructure, not forgetting changes to the contract itself.

The following diagram describes a simple CCP supported by HL7 GForge, the underlying implementation of the HL7 Project Homebase. The actual process may be more complex but this represents a comprehensive process that takes advantage of existing tools to automate the steps and ensure that the process is executed correctly.

Figure 7.4: Change Control Process

| login, select project | The "Tracker" tools (in the project's space in the Project Homebase) may be set up to allow anonymous issues but it is preferable that users be authenticated. |
| --- | --- |
| Enter Defect/Bug Report | The defect from a documentation error to a critical conceptual error in the standard specification. The defect may be detected during the testing and validation of a draft or final standard specification (informative or normative). |
| Enter Feature Request | The feature request refers to adding new capabilities to existing specification. This is similar to adding new requirements to the overall project. |
| GForge Change Request Ticket | The ticket is used to track the requester's change request through the resolution process. If approved for inclusion into a future release/ballot, then the ticket is transformed into a task assigned to a specific committee or project member. |
| Triage Requests (periodically) | This is a triage step intended to be conducted by the committee during its weekly conference call. This analysis will also determine if the change request is in scope for this committee or project. This step should categorize the severity of the change. Whether this change is substantive or not will be determined at this time. See the glossary for the definition of a substantive change. The change may be assigned to a specific person for evaluation. |
| Clarification needed | If the change request is ambiguous or too complex, the CCB may require more information from the requester. |
| Requirements clarification | This is an optional step intended to provide a requirements analysis for the original change request. This step is intended for enhancement requests, but defects may also take advantage of this clarification step. |
| Refer to another committee/project | If the change request does not apply to this committee, then the change request is referred to another committee or project. The requester is informed by automatically via e-mail that the change request was referred elsewhere. |
| Assign change request to team member | The change request can be converted into a task and assigned to a release. This is a feature supported by GForge. The resulting task is assigned to a person for resolution. |
| Provide Impact information | The impact is intended to determine the scope, duration, and resources needed to address the change. For instance, the change request may require the change of an information model or an interface specification. The scope of work and the skills required to complete it will be addressed at this step. If the solution has dependencies on other artifacts that are not completed yet, the impact analysis may require this solution to be deferred. If the change is substantive and requires another ballot the committee may decide to defer the resolution to a future ballot. |
| Announcement | The announcement tells the requester when the change will be addressed (e.g. Jan 2009 ballot). This is part of ballot intent announcement. |
| Artifact Review | The person who performed the changes provides a walkthrough to committee members. This could done in conjunction with a peer review. |
| HL7 Homebase SCM | Currently version control is provided by CVS. CVS is an open-source SCM tool. Software Configuration Management (SCM) is part of configuration management (CM). Roger Pressman states in his book, Software Engineering: A Practitioner's Approach, that software configuration management (SCM) is a "set of activities designed to control change by identifying the work products that are likely to change, establishing relationships among them, defining mechanisms for managing different versions of these work products, controlling the changes imposed, and auditing and reporting on the changes made." In other words, SCM is a methodology to control and manage a software development project. SCM concerns itself with answering the question: “Somebody did something, how can one reproduce it?” Often the problem involves not reproducing "it" identically, but with controlled, incremental changes. Answering the question then becomes a matter of comparing different results and analyzing their differences. Traditional CM typically focused on controlled creation of relatively simple products. Nowadays, implementers of SCM face the challenge of dealing with relatively minor increments under their own control, in the context of the complex system being developed. |
| Perform work to resolve the change as request | This step involves changes to models, documentation, methodology, etc. needed to address the change request. |
| Project Mgmt | The project management tool is intended to track the progress of ballots and projects in HL7. The project management tool available to committee members and change control board is currently Project Insight. |
| Review the changed artifacts | The requesters may have a preview of the artifacts changed per their request. |
| Publish in GForge | Publication means creating a new release in GForge by updating the "Documents" and "Files" tools appropriately. |
| Request Rejected | Enhancement request or those defect reports that are not defects but user misunderstanding. |

##### 7.4.1 Schedule work

For this step we recommend the use of project management tools (i.e., Project Insight). The scheduling decisions to assign the resolution of a change request to a ballot cycle depend on whether these changes are substantive or not, if dependencies exist, etc.  The "issue" is associated with a "task" and the task is associated with a specific ballot cycle.  This way the tools automate the tracking of issues and work items/tasks.

The following diagram details the process of including the resolution of an issue into a specific release/ballot cycle.

Figure 7.4.1: Schedule work

| Task | The task is associated with a ballot/release. The task is assigned to the person who is expected to make the artifact changes. The task may be part of a future ballot or the current ballot depending on the urgency of the issue. |
| --- | --- |
| Issue | The issue entered by the end-user |
| Add to ballot/release scope | The artifact affected by this change request becomes part of the ballot schedule. The committee must determine what artifacts are intended for publication and generate the new publication using the tooling already adopted. The change request is assigned to the task. The task is assigned to sub-project/ballot. |

### 7.5 Quality Criteria

The quality criteria for this process ensure the process was followed and the results are beneficial to the quality and speed of developing and correcting HL7 artifacts.

##### 7.5.1 Traceability to requirements

The principal way of demonstrating that a change request was fulfilled is to demonstrate traceability to the requirement or issue that originated it. A careful requirements analysis based on enhancement requests ensures that the changes made to the standard specifications can be traced to the change request initiated by the submitter.

### 7.6 Tools

This section demonstrates how we can use the HL7 Homebase portal and its ancillary tools (CCP) to record change requests and access the artifacts published by committees in response to new requirements or defect reports from HL7 membership.

The tools described in this section are used to automate the CCP.  Unlike other web-based collaboration tools (such as wiki, web-sites, etc.) they provide intrinsic support for change management functions.  This is an important difference that enables the seamless automation of CCP.

##### 7.6.1: Homebase Welcome Screen

HL7 Project  Homebase is a GForge-based tool used to manage project issues, version control, documentation, and release publication.

Figure 7.6.1: Homebase Welcome Screen

##### 7.6.2: My Personal Page

Once the user logs in, the following page will be visible.  Displayed in this page are projects of interest and the change requests originated by this user.

Figure 7.6.2: My Personal Page

##### 7.6.3: Project Space

Figure 7.6.3 shows the HDF Summary tab in GForge. This screen may be used to select whether a Bug (Defect or Technical Correction), Support Request (e.g. a publication error, missing files, etc.), or a new Feature is requested. To enter a new issue or change request, the users must select the "tracker" tool.

Figure 7.6.3: Project Space

##### 7.6.4: Feature Request

Figure 7.6.4 shows the "Feature request" screen. Each project may customize the drop-down lists and the fields that the submitter must complete. In this case HDF is used as an example. The submitter is selecting an "Ethnology area", specific to HDF, to indicate where the enhancement is needed.  In addition to pre-defined fields, the submitter may upload documentation before pressing the "Submit" button to complete the request.

Figure 7.6.4: Feature Request

##### 7.6.8: Assigning a Change Request to a Task

Once a change request is approved and determined to be in scope for the project by the Evaluator, its resolution will be part of a task, which in turn is part of a ballot cycle or release.  The project team may create a new task in the current/future ballot or assign the issue to an existing task.  The Task tools allow us to assign one or more issues from the tracker to the task.  This way we can validate that all issues are resolved when the task is completed.A task is a work item for the project team for a specific ballot. Unlike activities and milestones tracked in project management, these are very specific activities that change standard artifacts and tools. The project management tasks identify high-level life-cycle milestones rather than specific development, changes, and enhancements to standard specifications.

Figure 7.6.8: Assigning a Change Request to a Task

##### 7.6.9: Browse a Tracker (Feature Requests)

The projects and committees may provide a multitude of trackers (available in the "Tracker" tab). By default, the HL7 Homebase provides three trackers:"Bugs" (used to track defects and technical corrections)"Feature Requests" (for enhancements to existing standards or tools)"Support requests" (for problems using the standard publication or tools)For change control, only the "Bugs" and "Feature Requests" trackers are relevant. As seen here these trackers may be used to view/change current items, enter new items, and create reports on the existing items. The trackers are used by the committees to assign a change request (bug or feature request) to a member of the project for impact analysis. When the impact is completed, the item is related to a project task.

Figure 7.6.9: Browse a Tracker (Feature Requests)

##### 7.6.10: Traceability to requirements (defect, enhancement req)

A task is intended to address one or more change requests. The relationship between a task and one or more change requests is indicated in the "Related Tracker Items" section of the task detail dialogue.One of the great benefits of the Homebase tools is the provision for one or more change requests to be associated with a task and assigned to a project member. Unlike other tools the GForge "Tasks" tools allows us to group together several change requests in a single task. This allows us to address duplicate change requests or related change request. Before the tasks can be completed all the requirements referenced in the "Related Tracker Items" must be resolved.

Figure 7.6.10: Traceability to requirements (defect, enhancement req)

##### 7.6.11: Ballot Management using the "Tasks" tool

Each ballot may appear as a different "sub-project" under the "Tasks" tool. The committees/project may assign a task to any one of the available releases.

Figure 7.6.11: Ballot Management using the "Tasks" tool

##### 7.6.12: Gantt Chart for a ballot

Based on a subproject/ballot, the project team may create Gantt charts to communicate dependencies, progress, and identify scheduling issues in a graphical way. This Gantt chart addresses a single ballot and does not duplicate the type of chart created by the project management tools for the entire project/product lifecycle.

Figure 7.6.12: Gantt Chart for a ballot iteration

### References:

- HDF Project (HL7 Project Homebase)

http://hl7projects.hl7.nscee.edu/projects/hdf/

- Tutorials

http://hl7projects.hl7.nscee.edu/docman/?group_id=44

### Training

HL7 provides free training classes that introduce the CCP, project management, and associated tool training during the HL7 working group meetings (the next training session will be available in January 2008).